## Slide 1: Medicare Open Enrollment
Communications Plan
Office of Communications
Gwendolyn Green
Maya Newman
September 14, 2017

## Slide 2: Communications Objectives
Inform People with Medicare that Open Enrollment is the annual opportunity for them to review, compare and enroll in Medicare health and drug plans.
  With renewed emphasis on MA plans
Support a competitive marketplace of privatized health plans by encouraging competition.
Remind People with Medicare of the dates and deadline to review and compare: October 15 – December 7.

## Slide 3: Timeline – 2 Phases
Pre-implementation (Aug-Sept)
  Outreach to information intermediaries to prepare them to educate beneficiaries
Beneficiary Outreach (Oct-Dec)
  Educate beneficiaries about Open Enrollment Period (Oct 15 – Dec 7) and Medicare benefits

## Slide 4: Pre-Implementation Phase
Information Intermediaries
Partners
Providers
Plans
Stakeholders
State Health Insurance Programs (SHIPs)

## Slide 5: Open Enrollment Timeline - October
October 1
  Plan Marketing Begins
  Plan Finder Goes Live
October 15
  Open Enrollment Begins
  CMS Media Campaign Begins
Week of November 28
  Urgency Messaging Begins
December 7
  Open Enrollment Ends

## Slide 6: Key Messages
Open enrollment is the time to review your current health/drug plans and make changes if you want.
Review your coverage to see if you can find a better value. Even if you are happy with your current coverage, you might find something that’s a better fit for your budget or health needs.
  Plans can change their offerings every year, review to make sure your plan still works for you.
Medicare Advantage plans are offered by private insurance companies and combine all your benefits into one plan.

## Slide 7: Key Messages (continued)
Protect your personal information
Guard Your Card
Ensure your address is current with SSA

## Slide 8: Research
One pre and one post tracking survey
  Results regularly demonstrate a 20% increase in Open Enrollment knowledge among those who recall campaign.
  Pre- post- results also demonstrate a 20% increase in knowledge of Open Enrollment dates
Focus groups conducted to test ad concepts (report due 8/21)
Considerable message testing over the years.
  Major drivers of plan review and compare include the idea that plans change every year and that people may find a better plan or a lower cost. The second idea best if delivered in the first person “I compared and found a better deal.”

## Slide 9: Tactics: Paid Media Campaign
Paid Advertising – General Market
  National broadcast (Network TV, Cable TV, Radio)
  National paid search, digital video
Paid Advertising – African American
  National broadcast (Cable TV, Radio)
  Local print
Paid Advertising – Hispanic
  Geo-targeted radio, print
  National paid search

## Slide 10: Tactics: Earned Media
National
  Landscape of plans announcement (9/22)
  Media tours (radio and satellite)
  Article distribution
Regional
  Phone banks and other local events
  Interviews with Regional Administrators and other local spokespeople

## Slide 11: Tactics: Social Media
Facebook
  Posts Medicare Facebook page,
  http://www.facebook.com/Medicare
Twitter
  @MedicareGov, http://www.twitter.com/medicaregov
  Hashtag #MedicareOE
Medicare Blog
  http://blog.medicare.gov/

## Slide 12: Tactics: Communications Materials
SAMPLING BELOW:
http://www.cms.gov/Outreach-and-Education/Reach-Out/Find-tools-to-help-you-help-others/Medicare-Open-Enrollment.html
Ready-made articles (English & Spanish)
Editable event flyer (English & Spanish)
Live read public service announcement scripts (English & Spanish)
Social media graphics

## Slide 13: Tactics: CMS Information Channels
Medicare.gov
  Plan Finder and 5-star rating system
1-800-MEDICARE
  CSRs trained to use Plan Finder
YouTube
  Informational videos on CMS’ channel, http://youtube.com/user/CMSHHSgov
Publications
  Medicare & You Handbook
  Fact sheets

## Slide 14: Tactics: Local Outreach
SHIPs
Kickoff events
Ongoing Open Enrollment outreach events w/partners
Beneficiary counseling sessions
CMS Regional Office
Interviews with local media
Conference/Event promotion & participation

## Slide 15: Tactics: Educational Resources
Web-based Toolkit https://cms.gov/Outreach-and-Education/Reach-Out/Find-tools-to-help-you-help-others/Medicare-Open-Enrollment.html
Training Sessions
Open Door Forums
Conferences
Congressional Briefings
Listserv Messages

## Slide 16: Questions?