## Slide 1
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Training Segment 12
Monitoring Progress and Post Compliance Date Actions
An Informational Series on ICD-10 Planning and Assessment for State Medicaid Agencies
A Series of Topics on ICD-10 for State Medicaid Agencies:
What is ICD-10?
Regulatory Requirements
Benefits of Using ICD-10
Further Movement along the MITA Road Map - Use of Clinical Data and Interoperability
Effective Implementation of ICD-10
Potential Programmatic and Technical Problems
Impact on MITA Business Processes
Forming the Implementation Team
MMIS Funding Opportunities
Education and Training Processes
Partner and Vendor Considerations
Monitoring Progress and Post Compliance Date Actions
  ICD-10
  Planning and
  Assessment
Notes: <number>
The move from ICD-9 to ICD-10 is a significant change for State Medicaid Agencies. It will take considerable effort for Medicaid, and every health plan and provider in the country, to successfully accomplish the transition. However, there are considerable benefits to using the new code set.
We’ve prepared a series of training sessions especially for State Medicaid agencies which provide key information about the ICD-10 code set, how to use it, how to benefit from it, and what the implementation steps are. We hope to provide the information you need to effectively implement and to benefit from this major change to the coding of health care in the United States.
There are 12 Training Segments in the entire program.
<number>

## Slide 2
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Present a monitoring strategy to assure compliance is achieved
Present activities that will take place after the October 1, 2013 compliance date
Segment 12 – Monitoring Progress and Post Compliance Date Actions
Objectives of this Segment
Notes: <number>
The segment will focus on how the State Medicaid Agency can monitor its implementation process, determine if there are any issues, and stay on a path to timely compliance. We will also discuss some ICD-10 activities that will take place after the compliance date.

## Slide 3
Remember that this is a multi-year, wide-ranging project
Many parts, in fact most parts, of the organization are involved
It’s a long-range project that must be carefully managed to remain on time
Significant costs are expected, so budget planning, monitoring, and adjustments will be critical
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Scope of This Project
Notes: ICD-10 implementation may be the most complex project that the State Medicaid Agency has undertaken in a long time. It is far from an IT upgrade; it involves virtually every business process and every part of the organization, as well as every provider and other health plan. This is a four- to five-year undertaking, so it is important to have an overall project plan and monitor progress. Early estimates indicate that this will also be an expensive project, so budget estimation, planning, monitoring, and adjustment take on added significance.
<number>

## Slide 4
Implementation plan progress
Resource commitment and availability
Budgets
Vendor readiness
Partner readiness
Project quality
Relationship with other initiatives in the organization
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
What Must Be Monitored?
Notes: Because of the size and complexity of this project, careful attention must be paid to how the project is progressing, whether or not resources are available for each step, budget status and availability of funding, and the readiness of entities outside the organization. Also, it is critical that the quality of each work step be measured, and that the relationship of this project to other major initiatives in the organization be understood and followed. We will now look at each of these items in some detail to explain how best to monitor each one.
<number>

## Slide 5
Have a project plan developed and approved
Set up a regular reporting system so that the progress of each step can be tracked
Monitor tasks with current due dates and due dates some time in the future
Identify obstacles and slippages early enough to deal with them
Automated project management and tracking tools are very useful for this
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Implementation Plan Progress
Notes: First, determine the status of the overall implementation plan. It is absolutely imperative that a detailed project plan, with each task clearly identified and assigned, be created and approved by the organization. Once this is accomplished, a regular reporting system must be set up so that the progress of the project against the plan can be tracked. Since ICD-10 implementation is such a large effort, it is recommended that a Project Management Office (PMO) be established and charged with the responsibility of monitoring and reporting on the status of the project.
It is important to monitor not only current tasks, but also tasks with due dates in the near- to mid-term future, so that progress can be assured. This will enable the organization to identify obstacles to progress (and current and upcoming slippages), so that corrective actions can be taken to deal with them. Keeping the project on target throughout its lifetime will enable a much smoother implementation.
There are a variety of automated project management and tracking tools available. Given the size of this project, these should prove very useful. The NCHICA/WEDI timeline can be used as a basic framework for a project plan.
<number>

## Slide 6
The “right” resources must be available at the “right” time
Project plan should identify these
Constant emphasis should be placed on the priority of this project
Get the commitment and adhere to it
If issues arise, look at alternatives:
  Contracting
  Other state agencies
  National organizations
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Resource Commitment and Availability
Notes: The key to a smooth implementation involves assuring the availability and commitment of resources to each step in this project. It is imperative that the project plan identify both the amount of resources and the type of resources that are required to complete each step of the plan. Once identified, project managers must assure that these resources are made available, and that they remain available for each step. Top management must continue to emphasize the priority of this project (which should be quite high given the federal mandate and the need to interact with the outside health care community).
If there is an issue with resources – and it should be identified early – alternative solutions must be considered to keep the project on time. Some of these alternatives could include utilizing other agencies within the state government for additional resources, relying upon information from national organizations on how best to accomplish certain tasks, or perhaps contracting certain resources.
<number>

## Slide 7
Focus on the long-term effort, assuring that money will be available for the entire project
Be aware of year-to-year changes in state budgets and unforeseen events
Spreading costs throughout the life of the project should allow a less variable budget
If money becomes available from other projects, having an established plan may allow you to get that money
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Budgets
Notes: ICD-10 is a multi-year effort, which makes budgeting a difficult task in the state environment. It may be difficult to get a budget commitment for the entire term of the project, but estimating the budget for the entire project and attempting to spread costs out through the project may help to limit the budget needs in any one year. Events may occur in any one state that can jeopardize funding, or make more funds available. Project managers should be aware of such events.
It would also be wise to look to other projects within the state to see if additional money may be available, or to combine efforts with other state departments, so that costs can be shared.
<number>

## Slide 8
Need inventory of vendors
Get commitments from vendors as to their delivery dates – Assure that your project plan dates are met.
Reconfirm progress toward the vendor delivery date
Look at sequencing of vendor products and assure that it is correct
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Vendor Readiness
Notes: Many states rely on vendors for their IT and other activities. An early step in the implementation process would be to identify all of the vendors that will impact the project. Once identified, you should get a commitment from each vendor as to when they will deliver their product as “ICD-10 ready” for your plan. Make sure that you get a commitment that enables you to meet the dates in your project plan.
Once you have that initial commitment, note it. Then, reconfirm the vendor’s progress toward their committed delivery date. Look for evidence of progress (beta software tests, interim products, etc.).
There are some relationships among your vendor products – for those products that depend on others, make sure that the sequencing of dates is correct.
<number>

## Slide 9
Critical for testing
Monitor partner readiness
Focus on those partners that will enable you to do the “best” testing; the widest variety of situations
Prioritize your trading partners and focus on the most important and largest volume
This will feed into your testing plan
If partner readiness is slipping, take some immediate actions
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Partner Readiness
Notes: Remember that every health plan, provider, and health care clearinghouse is going through the ICD-10 implementation process. You cannot assure that your implementation is successful until you have tested with partners to measure that the exchange of transactions is successful and that transactions are processed accurately. The external testing piece of your implementation plan is totally dependent on working with trading partners.
Keep informed of industry progress toward implementation, especially your major trading partners. Focus early on partners that will enable you to do robust testing of your systems and processes. Look at your implementation plan and make sure your external testing is on track. If some of your partners will not be ready early enough to do testing, look at alternatives.
<number>

## Slide 10
There are a number of tasks that will become important after the Oct 1, 2013 date
This project does not end on Oct 1, 2013. In fact, there will be tasks that will stretch 2-3 years beyond the compliance date
Include these tasks in your overall project plan, and budget for them
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Post Compliance Date Actions
Notes: So, what happens after October 1, 2013? This project is far from over. There are a number of tasks that cannot start until after the compliance date, but are also critical to the success of the project. Some of these tasks will extend 2-3 years after Oct 2013. Remember to include these tasks in your overall project plan and budget for them.
<number>

## Slide 11
Assuming you are ready:
  Monitor your processes
    Timeliness of transaction processing
    Accuracy of transaction processing
    Staff knowledge of ICD-10 processes
    Number of calls to provider help desk
  Monitor your trading partners
    Who is/isn’t working in ICD-10
  Monitor vendor products
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
What to Do after Oct 1, 2013
Notes: We will assume that you are ready to transact business using ICD-10 codes for services on and after Oct 1, 2013. One of the first items to do is some very close monitoring of your processes. Are transactions using ICD-10 being processed in a timely manner? Are they being processed accurately? How is staff responding to the new code set? Are they operating successfully? Monitor calls to your provider help desk. It is expected that the volume of such calls will rise dramatically during the first few months of ICD-10. Plan for that.
Monitor your trading partners. All should be using ICD-10 based on service date. Are they? Is anyone using ICD-10 for services prior to Oct 1, 2013? How are you reacting to improper code set uses?
Look at all of your vendor products (remember your inventory – use it!). Are all operating successfully with ICD-10?
<number>

## Slide 12
Gather data on ICD-10 trends
  Does data make sense?
  Are you seeing unexpected results in reimbursements or types of diagnoses?
  Are targeted programs working as expected, or do you have too many or too few participants?
  Look at edit results – Are you catching the right claims or not?
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
What to Do after Oct 1, 2013
Notes: As more and more transactions come in with ICD-10 codes, start gathering some trend data. Do the diagnosis and inpatient hospital procedure trends make sense? You should have a general idea of diagnosis trends from ICD-9 data; the ICD-10 data should not break dramatically from general trends (number of cases of asthma, diabetes, heart disease, etc.). Are there unexpected reimbursement changes – by provider type or locality?
Look at your targeted disease programs. Are they still working as expected? Are you identifying more participants than expected?
Monitor your claim edit results. Are you properly accepting and rejecting claims for medical review, fraud and abuse, etc.?
<number>

## Slide 13
Be especially vigilant for abusive or fraudulent activities
Communicate with partners, other state Medicaid agencies, and other plans about their experiences
Need to think about trending data from ICD-9 to ICD-10 and how to accurately measure trends
Work with any trading partners who have not made the switch or are having great difficulty
Be aware of any necessary vendor patches
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
What to Do after Oct 1, 2013
Notes: It is expected that the switch to ICD-10 will encourage attempts at fraudulent or abusive practices, since the experience in dealing with the codes does not exist. Some initial work should already have been done to develop some early screens, but it may not be known how accurate those screens are. Be vigilant.
Communicate with your trading partners, other state Medicaid agencies, and health plans in your state on their experiences. Share lessons learned.
You will have to determine how best to handle claims history for trending from ICD-9 to ICD-10. Look at ways to accurately measure trends. We cannot wait 2-3 years to gather ICD-10 trend data on which to make decisions.
Also, keep in close contact with vendors who may be distributing “patches” to their products if they discover issues with ICD-10.
<number>

## Slide 14
Look at more ways to use the information in ICD-10 for making program improvements, improving beneficiary health, and being more cost-effective with Medicaid funds
Don’t “forget” about ICD-10 just because the compliance date has passed
There will be periodic (annual?) code updates, so plan for them
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
And as We Move on...
Notes: And as you move on in the use of ICD-10, keep looking for more ways to use the information that you are receiving in the ICD-10 codes. There will be further opportunities for improving beneficiary health, making program improvements, fine tuning edits, and being more cost-effective with Medicaid funds. The more detailed codes should allow you to target specific disease areas for improvements. Don’t forget about these codes just because the compliance date has passed.
And, just as we have seen with ICD-9, there will probably be periodic and annual updates to the codes, so plan for them.
<number>

## Slide 15
The ICD-10 project is a complex undertaking that must be closely monitored to ensure success
Use your project plan and keep it updated
Monitor not only your activities, but those of partners and vendors
The project does not end on Oct 1, 2013. Plan for continuing activities.
07/30/26
Segment 12 – Monitoring Progress and Post Compliance Date Actions
<number>
Summary
Notes: Effectively monitoring your project plan and reacting to delays and changes is necessary with such a complex undertaking as ICD-10 implementation. There are many moving parts that must be watched, including your own staff and activities, and those of your vendors and trading partners.
There will also be work after Oct 1, 2013. We have pointed out several activities that will be occurring after the compliance date. You must include those in your planning.
<number>