## RISK IDENTIFICATION & ANALYSIS
FUNDING No.: |  | FULL PROJECT NAME: |  |  | PROJECT MANAGER: |  |  | TECHNOLOGY DEPLOYED:
PRINT ON LEGAL SIZE PAPER
RISK ID | DATE IDENTIFIED | RISK SUBMITTER | RISK TYPE | RISK CATEGORY | RISK DESCRIPTION & IMPACT | RISK PROBABILITY | RISK IMPACT | RISK EXPOSURE | TASK ID | ASSOCIATED RISKS

## Sheet3 (hidden)
Technical
Sponsorship
Communications
Schedule
Budget
Contracts
Scope
Accept
Transfer
Mitigate
Avoid
Share
Exploit
Enhance

## RISK RESPONSE PLAN
FUNDING No.: | 0 | FULL PROJECT NAME: | 0 |  | PROJECT MANAGER: | 0 | TECHNOLOGY DEPLOYED:
PRINT IN LEGAL SIZE PAPER
RISK ID | RISK TYPE | RISK EXPOSURE | RISK OWNER | RISK TRIGGER DESCRIPTION | RISK TRIGGER OCCURRENCE | RISK RESPONSE TYPE | RISK RESPONSE DESCRIPTION | RISK STATUS
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0

## PROBABILITY & IMPACT MATRIX
Probability |  | Impact
H (High) | 61-100%, Certain, Very Likely to Occur | H (High) | 61-100% Impact on Scope/Schedule/Cost/Customer Satisfaction
M (Medium) | 31-60%, More Likely to Occur | M (Medium) | 31-60% Impact on Scope/Schedule/Cost/Customer Satisfaction | PROBABILITY | Probability & Impact Matrix
L (Low) | 0-30% Certain, Least Likely to Occur | L (Low) | 0-30% Impact on Scope/Schedule/Cost/Customer Satisfaction
The probability and impact scale is outlined above. It serves as an example to be tailored for every project. The High (H), Medium (M) and Low (L) thresholds are to be tailored for the assessment of probability and impact of the identified risks. As determined by your project stakeholders, a high probability has a high likelihood of occurring. A medium probability has a medium likelihood of occurring. A low probability has a small probability of occurring. Please define the numerical percentage ranges of what your project stakeholders deem to be in the H, M and L probability ranges. The impact column should delineate the likelihood that risks will have an effect upon the project's scope, schedule, cost, and customer satisfaction. A high impact means that if the risk is to occur, it will have a significant outcome on the project in terms of scope, schedule, cost and/or customer satisfaction. A medium impact has a medium consequence to the project if the risk is to occur. A low probability has a smaller consequence to the project. Please define the numerical percentage ranges for your H, M and L impact thresholds. When editing the table above, please do not delete or update the H, M, and L columns (columns above in the dotted areas.) Once your numerical percentages and thresholds for H, M, and L are defined, please color code the Probability & Impact Matrix on the right. The matrix represents the different risk exposure levels (Risk Exposure = Risk Probability x Risk Impact.) For example, HM = H (Probability) * M (Impact.) The color codes will be used to bring the attention of the project team members assigned to project risk management. In the example on the right, the HM and HH were color coded red. The color red could be used for risks to be monitored later. Under the matrix, there is a placeholder to be used as a legend to define the use of your different color codes. |  |  |  |  | H | HL | HM | HH
[5 empty] | M | ML | MM | MH
[5 empty] | L | LL | LM | LH
[6 empty] | L | M | H
I M P A C T

## MANUAL
INSTRUCTIONS FOR THE RISK REGISTER
1. Overview
2. Risk Management Process
2a. Risk Identification
2b. Qualitative Risk Analysis
2c. Quantitative Risk Analysis
2d. Risk Response Planning
2e. Risk Monitoring and Control
1. Overview
Risks are events that can happen or take effect in the future course of a project. There is the possibility that what we call risks will influence the outcomes of the project. When these risks occur, their impact can take several forms that can jeopardize the schedule, cost, performance, scope and customer satisfaction along with many other crucial factors, of primary importance to the project and organization.
2. Risk Management Process
The Risk Management Plan is a component of the Project Management Plan. The Risk Management Plan documents the processes of project risk management. The template available for the Risk Management Plan enables the project manager and relevant stakeholders to document how the five risk management processes will be carried out in the form of methods and tools. Roles and responsibilities for managing risks are to be defined and documented in that template, as well as any plans to improve the risk management process.
2a. Risk Identification
In this report, the first tab "RISK IDENTIFICATION & ANALYSIS" is available for the project manager or relevant stakeholder to document the risks identified in the project. Please feel free to click on the links below to see where these fields are located in this template.
Risk ID
Date Identified
Risk Submitter
Risk Type
Risk Category
Risk Description & Impact
Task ID
Associated Risks
2b. Qualitative Risk Analysis
The purpose of the qualitative risk analysis process is to determine which of the identified risks will deserve a response plan and eventually be placed on a watch list. The qualitative assessment begins with the tailoring of the Probability & Impact Scale and Matrix. Please see the tab "PROBABILITY & IMPACT MATRIX".
After the probability and impact matrix scale and the matrix are defined by the project stakeholders, it is time to evaluate each risk for probability and impact. Please feel free to click on the links below to see where these fields are located in the template.
Risk Probability & Impact Matrix
Risk Probability
Risk Impact
Risk Exposure
2c. Quantitative Risk Assessment
The tool and method used for quantitative risk assessment is not available in this template. However, feel free to use additional tools necessary to perform quantitative risk analysis, and as deemed suitable for your project.
2d. Risk Response Planning
Risks can take effect throughout the lifespan of the project. To prevent the risks from realizing, risk triggers are identified in advance, and listed in the risk register. A risk owner is assigned to look out for the risk triggers, and risk response plans are outlined so that the risk owner can take appropriate actions when the risk triggers occur. The tab "RISK RESPONSE PLAN" pulls data identified from the tab "RISK IDENTIFICATION & ANALYSIS." Please feel free to click on the links below to see where these fields are located in the template.
Risk Owner
Risk Trigger Description
Risk Response Type
Risk Response Description
2e. Risk Monitoring & Control
During Risk Monitoring and Control, the risk owner keeps an active eye for the risk triggers. Meetings are held to go over risk status. The purpose is to ensure that the project is on track, and that opportunities and threats are addressed appropriately.
Risk Trigger Occurrence
Risk Status

## INSTRUCTIONS
FUNDING No.
The funding number is assigned by the OFM (Office of Financial Management) once the project is approved for funding.
PROJECT MANAGER
Individual responsible for creating, updating and maintaining the integrity of the risk register. Individual assigned with the responsibility of documenting risks and orchestrating project risk updates with the risk owners.
TECHNOLOGY DEPLOYED
Technology deployed is the category or component of a system under development in this project. The categories of technologies currently available are Mid-tier (application), Desktop, Mainframe, Database, Infrastructure, Office Automation or Telecommunications.
RISK ID
A unique identifier in a numbering system assigned to a risk. The identifier should be used for reference or for cross-reference in the future among project team members and future project stakeholders in search of historical information. Example: R01, R02, R03...
DATE IDENTIFIED
The original date when the risk was originally brought to light, or identified.
RISK SUBMITTER
The name of the individual who identified and submitted the risk to bring the attention of project stakeholders.
RISK TYPE
Risks can be positive (opportunity) or negative (threat.) An example of an opportunity is "The latest UML software will reduce programming efforts by 30%, thus decreasing the amount of hours needed to produce the software." An example of a threat is "A tornado can hit the remote city of Alabama as forecasted where the software developers are."
RISK CATEGORY
If the risk is to occur, it will come from a root source. From nature, it can relate to the lack or abundance of technology, sponsorship, communications, schedule, budget, contracts and scope. For example, "With the support of sponsors, there will be enough resources dedicated to the project." The example references a positive risk or opportunity.
RISK DESCRIPTION & IMPACT
The risk description should state what event can take place in the future, and the impact it will have on the project.
RISK PROBABILITY
Please see Probability & Impact Matrix
RISK IMPACT
Please see Probability & Impact Matrix
RISK EXPOSURE
Please see Probability & Impact Matrix
TASK ID
The task ID is the task defined in the network diagram, activity list or schedule that will be affected by the risk. As an example, "There is not enough feedback from end-to-end user testing when the codes are updated and changed. Members from the unit testing group will have the older codes, which will generate outdated and irrelevant applications in the future. The impact will be to the quality of the product in the next release." The unit testing tasks are the affected tasks, and their relevant Task IDs should be identified and documented in this case.
ASSOCIATED RISKS
Associated risks are inter-related. If an event is to take place in the near future, these other events will also take place. As an example and not a fact, "If the commercial rental rates decrease in the South where the offsite contractors are, there will be an impact on the overhead costs in the facilities of New Mexico, Arizona and Georgia" which could be associated with "the future possibility that the towns of New Mexico, Arizona and Georgia will attract less skilled and efficient employees thus harnessing the outcomes of a high-tech project."
RISK OWNER
The risk owner is the individual assigned to the project who tracks the risks for triggers.
RISK TRIGGER DESCRIPTION
Risk triggers are indications that the risk is to occur. In this section, please describe what these indications could be. For example, a news release could be a positive or negative risk trigger that an event is yet to occur. A certain financial indicator used in forecasts (such as EVM) are among the several triggers that can be identified by project stakeholders.
RISK TRIGGER OCCURRENCE
The risk trigger occurrence communicates if the risk has or has not taken place.
RISK RESPONSE TYPE
Risk responses are chosen according to their risk categories. If a risk is positive or is to bear an opportunity, the risk response type could be to accept the risk, exploit the risk or enhance the risk. If a risk is negative or it is a threat, the risk response type could be to mitigate or avoid the risk. For both situations, one can chose to transfer and share the risk with a different party. Sharing or transferring a risk can be used when the resources and expertise are limited, though many other cases lend to the option for choosing these risk responses.
RISK RESPONSE DESCRIPTION
From the choice selected for "risk response type," please elaborate yet outline how you plan on responding to the risk. An example is to "Purchase software when the company's marketing news release is made public to bring the efficiency factor up by 30%."
RISK STATUS
Risk status are updates to indicate whether risk triggers have occurred and/or addressed (resolved), or not taken place yet but is still to occur in the future (open).