## Slide 1: MARx Redesign & Modernization Readiness Review

## Slide 2: MARx R&M Key Dates
<number>
Date | Activity
April 4, 2011 | Plan users may register for UI Update Role via IACS
April 8, 2011 | Plan Data Due Date – May 2011 payment
April 13, 2011 | Last date to submit files in old MARx format [8:00 pm Est.]
April 15, 2011 | Weekly reports available [last of the weekly TRR]
April 18, 2011 | Go Live – MARx accepts batch files in new format only; UI in read-only mode
April 19, 2011 | UI in update mode First Daily TRR delivered
April 22, 2011 | Monthly Report for May payment – old format Last Monthly TRR
May 6, 2011 | Payment cut-off for June 2011 CPM
May 20, 2011 | Monthly Reports – new format
Notes: <number>

## Slide 3: CMS Activity
Bring systems down
Data conversion to new structure
Shakedown
Recover systems
Go live!
<number>
Notes: <number>

## Slide 4: MARx Interfacing and Downstream Systems
<number>
Exterior partner
Immediate business partner
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Notes: <number>

## Slide 5: MARx Interfacing and Downstream Systems Shut Down Starting: Wed. April 27th – 8pm
<number>
Exterior partner
Immediate business partner
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Active system shutting down
Partial shutdown
Notes: <number>

## Slide 6: MARx Interfacing and Downstream Systems Shut Down continuing: Thurs. April 28th – 8pm
<number>
Exterior partner
Immediate business partner
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Active system shutting down
Already shut down
Partial shutdown
Notes: <number>

## Slide 7: MARx Interfacing and Downstream Systems Shut Down continuing: Fri. April 29th – 12 Noon
<number>
Already shut down
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Active system shutting down
Notes: <number>

## Slide 8: MARx Interfacing and Downstream Systems Data Conversion: Fri.-Sat. April 30th – 16th
<number>
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Active system shutting down
Already shut down
Notes: <number>

## Slide 9: MARx Interfacing and Downstream Systems Shakedown/Restart Beginning: Sun. May 1st
<number>
Already shut down
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Undergoing data conversion
Parts of system coming back up
Notes: <number>

## Slide 10: MARx Interfacing and Downstream Systems Go Live: Mon. May 2nd
<number>
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Undergoing data conversion
Parts of system coming back up
Still up from yesterday
Already shut down
Notes: <number>

## Slide 11: MARx Interfacing and Downstream Systems Tues. May 3rd
<number>
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Undergoing data conversion
Parts of system coming back up
Still up from yesterday
Already shut down
Notes: <number>

## Slide 12: MARx Interfacing and Downstream Systems Full Operations: Wed. May 4th
<number>
System within CMS
Process
Utility tool that transforms data
Data Mark
Database
Undergoing data conversion
Parts of system coming back up
Still up from yesterday
Already shut down
Notes: <number>

## Slide 13: Plan Readiness
Have you:
Reviewed the Handbooks?
Adjusted to the new formats?
  Split TC 74 into discrete TC
  New TC 76; residence address
  Support multiple 4Rx periods within an enrollment
Reviewed the new TRC and taken appropriate steps?
Trained your staff?
  This effort goes beyond your IT areas
<number>
Notes: <number>

## Slide 14: Plan Readiness - Continued
Prepared for Daily TRR?
  “000” TRC for no activity
  Test file TRR (Feb. 28th)
  Original input provided
Prepared for BCSS Changes?
Thought about your UI Update users?
  Quality Review monitoring
<number>
Notes: <number>

## Slide 15: After Implementation
The MAPD Help Desk is your technical resource
  Non-technical questions go to your AM
Please review the handbooks before calling the MAPD Help Desk
CMS monitoring of system performance and business outcomes
<number>
Notes: <number>

## Slide 16: RPC – Quality Review (QR)
Overview:
  Monthly Quality Reviews (QR) of all plan-submitted transactions through the MARx User-Interface (UI)
Goals:
  Ensure actions submitted through the MARx UI are valid and supported with plan documentation
  Ensure plans maintain strict adherence to CMS policies and requirements
<number>
Notes: <number>

## Slide 17: RPC – Quality Review
Process Summary:
  Performed by the Retroactive Processing Contractor (RPC)
  Process is similar to the existing Quality Review (QR) Process (formerly called Probe Study) for Payment Validation retroactive transactions (SCCs, Medicaid & ESRD)
<number>
Notes: <number>

## Slide 18: RPC – Quality Review
  Monthly random sample of all plan UI actions
  Plan’s POC will receive a report from the RPC listing sampled cases
  Plans will have 7 calendar days to submit complete required documentation
  RPC has 35 days to review documentation supplied for sampled transactions
<number>
Notes: <number>

## Slide 19: RPC – Quality Review
  Documentation requirements are the same as today (subject to updates)
  Documentation that does not meet the guidelines will result in a failed review
  Plans that do not submit documentation timely will receive a failed review
  Plans that fail a Quality Review are subject to suspension of all Parent Org MARx UI update privileges
<number>
Notes: <number>

## Slide 20: Questions?
<number>
Notes: <number>