## Slide 1: CMS Earned Value Management Self-paced Orientation
Depress the space bar to continue, F5 to start
Note on accessibility: Attention is called to the words marked between asterisks as follows.
* Attention called out here *

## Slide 2: Syllabus
Earned Value Management History
EVM – What Is It ?
Basic EVM Metrics
When Can EVM Best Be Used ?
Requirements
  OMB
  HHSAR
  HHS CPIC
  Reporting
Depress the space bar
to continue

## Slide 3: Earned Value History - 1
Since the 1890s, industrial engineers have compared physical factory output to:
  Actual costs to determine cost variance
  Planned physical output to assess schedule variance
Starting in 1957, the U.S. Navy, then the Air Force, then the entire Department of Defense, adopted schedule, then cost, performance measures for projects and contracts
In 1967, DoD Instruction 7000.2, “Performance Measurement for Selected Acquisitions,” imposed 35 Cost/Schedule Control Systems Criteria (C/SCSC) on the defense industry

## Slide 4: Earned Value History - 2
In 1995, The National Defense Industry Association (NDIA) took on the task of reviewing / rewriting the 35 criteria to make them more compatible with private industry practices
In 1996, DoD accepted the NDIA’s 32 guidelines
In 1998, the 32 guidelines were incorporated into ANSI/GEIA Standard GEIA-EIA-748
Since then, many federal agencies have adopted ANSI Standard 748 as their reference for EVMS’
In 2004, the NDIA “Intent Guide” was published to expand on Section 2 of ANSI Standard 748

## Slide 5: Earned Value Management: What Is It?
An integrated method for monitoring cost, schedule, and performance, in which
Work is planned, scheduled, and budgeted in time-phased increments to yield a baseline, and
Performance is measured against the baseline
It provides timely, traceable contract performance data to support decision-making
It answers the question, “What did we get for what we spent?”

## Slide 6: EVM: A Project Management Tool
Uses Cost And Schedule Data
  To Compare Performance To Baselines
  For Trend Analysis, Forecasting, History
  By Total Project, Work Breakdown Structure, Or Organizational Breakdown Structure
Does Not Replace
  The Critical Path Method
  Risk Management
  Quality Management

## Slide 7: Basic EVM Metrics - 1
BCWS Budgeted Cost of Work Scheduled
Value of work planned to be accomplished by now
= PLANNED VALUE
BCWP Budgeted Cost for Work Performed
Value of work accomplished to date
= EARNED VALUE
ACWP Actual Cost of Work Performed
Cost of work accomplished to date
= ACTUAL COST
BAC Budget At Completion = the budget
EAC Estimate At Completion
Notes: HANDOUT: EVM Card

## Slide 8
Basic EVM Metrics - 2
Time
Earned Value (BCWP)
$
Time Now
EAC
BAC
Risk
Cost Var.
For EVM, baseline cost is plotted against time. The Planned Value is the baseline against which progress is measured. The Budget At Completion (BAC) is the sum of the planned costs.
The Earned Value is the budgeted cost of the work performed to date
A difference between the Planned Value and the Earned Value is called Schedule Variance
A difference between the Earned Value and the Actual Cost is called Cost Variance. From a trend in AC, an Estimate At Completion (EAC) can be calculated.
The Actual Cost is the actual cost of the work performed to date
Cost variance and schedule variance are the primary risks for any project, and are the primary focus of EVM
Actual Cost (ACWP)
Schedule Var.
Planned Value (BCWS)

## Slide 9: Key Performance Metrics
CV% - Cost Variance Percentage - The relationship of the earned value to the actual cost of the work done to now, as a percentage [(BCWP minus ACWP) BCWP]
SV% - Schedule Variance Percentage - The relationship of the cost of work actually done to the cost of the work planned to be done [(BCWP minus BCWS) BCWS]
VAC% - Variance at Completion Percentage – How far off are the projected completion costs from the budget. [100 (VAC BAC) where VAC is BAC minus EAC.
These three metrics are monitored by HHS.
OMB’s Federal IT Dashboard monitors its own versions of CV% and SV% calculations.

## Slide 10: What Does This Mean ?
From 40 Years Of DoD Experience:
  Can accurately statistically forecast final cost (EAC) as early as 15% of the way into a project 1
  Once a project is 15% or more complete, the overrun at completion will not be less than the current overrun 2...but you can keep it from getting worse
  Once a project is 20% complete, the cumulative cost performance index does not vary from its current value by more than 10% 3
  Bottom Line: Use EVM to identify small problems early, before they become large problems !
1 “A-12 Administrative Inquiry” memorandum by Chester Paul Beach, Jr. (Washington DC: Office of the Under Secretary of Defense for Acquisitions, November 28, 1990)
2 Figure 4.2, Earned Value Project Management by Quentin W. Fleming and Joel M. Koppelman (Newton Square PA: Project Management Institute, 2005), pp. 40-41
3 “Cost Performance Index Stability” by Major David S. Christensen, Ph.D., and Captain Scott R. Heise (National Contract Management Association Journal, 25:7-15, 1993),
pp. 7 and 13

## Slide 11: When Can EVM Best Be Used ?
Projects Need To Have:
  Clearly defined objectives
  A clearly perceived plan to achieve goals
  Formalized management structure and processes
  Cost and time constraints
Milestones

## Slide 12: Requirements: OMB - 1
“…Agencies…must:
  “Institute performance measures and management processes monitoring and comparing actual performance to planned results. Agencies must use a performance-based acquisition management or earned value management system, based on the ANSI/EIA Standard 748, to obtain timely information regarding the progress of capital investments. *The system must also measure progress towards milestones* in an independently verifiable basis, in terms of cost, capability of the investment to meet specified requirements, timeliness, and quality. …”
Section 300.5, Part 7, OMB Circular A-11

## Slide 13: Requirements: OMB - 2
“*Major* investment means a system or acquisition requiring special management attention
  Because of its importance to the mission or function of the agency, a component of the agency or another organization;
  Is for financial management and obligates more than $500,000 annually;
  Has significant program or policy implications;
  Has high executive visibility;
  Has high development, operating, or maintenance costs;
  Is funded through other than direct appropriations;
  Or is defined as major by the agency’s capital planning and investment control process
“Systems not considered ‘major’ are ‘non-major.’ “
Section 300.4, Part 7, OMB Circular A-11

## Slide 14: Requirements: OMB - 3
“...Agencies are expected to achieve, on average, *90 percent* of the cost, schedule and performance goals for major acquisitions.
“Agency Heads must review major acquisitions not achieving *90 percent* of the goals to determine whether there is continuing need and what corrective action, including termination, should be taken;”
Hence, the HHS requirement for a corrective action plan when CV% or SV% exceeds 10%
Section 300.5, Part 7, OMB Circular A-11

## Slide 15: Requirements: The HHSAR - 1
Section334.201(a): “For acquisitions for development designated as *major* in accordance with both OMB Circular A-11 and HHS policy on major acquisitions; for acquisitions that involve *substantial development, modification or enhancement;* or for acquisitions that involve *significant upgrade* of operational or steady state systems or programs, use of an Earned Value Management System (EVMS) is required”
Section 352.234-2(b) “If the offeror proposes to use a system that currently does *not* meet the requirements of paragraph (a) of this provision, *the offeror shall submit a comprehensive plan for compliance* with the guidelines.”
  The contractor uses the EVMS it has; reports on progress

## Slide 16: Policy: The HHSAR - 2
16
Section 334.201, Policy
  Cost Reimbursement, FPIF contracts ≥ $10 M
    EVM *System* must comply with all 32 guidelines of ANSI Standard 748
  FFP, LOE, T&M, Labor Hour contracts ≥ $10 M
    EVM System must comply *only* with the Schedule guidelines of ANSI Standard 748
  Including option years
Section 334.203: Standard contract clauses must be used

## Slide 17: Requirements: The HHSAR - 3
Section 334.201(d): “(c) When full EVM is required on a prime contract, it *applies to subcontracts* issued there under [sic] ... However, if the prime contract requires the use of only partial EVM, any *subcontracts* to which EVM is made applicable, because of dollar value, contract type or subject matter, shall require only partial EVM.”
Section 334.202(a): “An *IBR* normally should be conducted as a post-award activity.”
Section 352.234-2(b)(3) “The *Contracting Officer* will review the offeror’s EVMS implementation plan prior to contract award.”
  Section 352.234-3a: “The Contractor shall submit EVM *reports* in accordance with the requirements of this contract.”

## Slide 18: Policy: HHS IT CPIC (Capital Planning & Investment Control)
HHS OCIO Policy for Information Technology Investment Performance Baseline Management, December 22, 2010 (HHS-OCIO-2010-0007)
  “All HHS Major and Tactical IT investments and their associated IT projects throughout their entire lifecycles” (§3)
  “All HHS Supporting IT investments with budget year costs equal to or greater than $1M...” (§3)
  *Monthly* cost & schedule reporting (§4.2.9.1)
  *IBR* at the end of the EPLC Planning Phase for each IT project comprising the investment (§4.2.11)
  *Annual Operational Analysis* for O&M (§4.4.1)

## Slide 19: Reporting: Cost - Use The IPMR
Monthly
Integrated Program Management Report (IPMR) - Formerly known as Contract Performance Report (CPR)
  Minimum is Format 1 and Formats 5-6
  DD Form 2734/1 through 2734/4 and Formats 5-7
  http://quicksearch.dla.mil/basic_profile.cfm?ident_number=278901&method=basic
  Data Item Description DI-MGMT-81861
  What data goes in each item of each format
  http://www.acq.osd.mil/pm/currentpolicy/cpr_cfsr/CPR%20Final%203-30-05.pdf

## Slide 20: Integrated Program Management Reports
DD Form 2734/1 through 2734/4 and Formats 5-7, June 20, 2012
IPMR DID (Data Item Description) DI-MGMT-81861, 20120620
Formats 1 and 5-6 Mandatory
AS-OF
DATE
CURRENT
CUMULATIVE
B
C
W
S
B
C
W
P
A
C
W
P
1.0 The Project
1.1 Project Managbment
12 High-level One
1.2.1 This
1.2.2 That
1.2.3 The Other
1.3 High-level Two
1.4 High-level Three
CV
SV
(BCWP x
100) ÷
BAC =
Actual %
ONE WAY TO GET
ACTUAL PERCENT COMPLETE
BAC
Data in
Green
is entered
into OPPM
(BCWS x
100) ÷
BAC =
Planned %

## Slide 21: Integrated Master Schedule
ANOTHER
PLACE TO
FIND ACTUAL PERCENT COMPLETE

## Slide 22: Reporting: Schedule
Scheduling Software
  Microsoft Project 2010 is CMS’ standard
Calendar
Gantt Chart
Units Complete Method
  Equal increments may be appropriate, where the time periods’ costs are similar
  For O&M (operations and maintenance; “steady-state”) Phase activities only

## Slide 23: Reporting: Monthly PMT Data Entry
Oracle Primavera Portfolio Management
For each *current Activity*
  Total Costs Actual
  Planned % Complete
  Actual % Complete
  Start Date Projected
  Completion date Projected
And, if the Activity just started or just ended:
  Start Date Actual, or
  Completion Date Actual

## Slide 24: “Activities” In PMT - 1
OPPM Activities should represent manageable chunks of the work, but not be so detailed as to make reporting onerous
  OPPM is the tool for 1) justifying the investment for funding and, once approved and funded, 2) providing CMS senior management, HHS, and OMB with monthly snapshots of how well the investment is being managed . . . against the approved Plan in OPPM
  OPPM usually is not the tool that investment teams use to daily manage their projects
The Activities should be recognizable, easily identifiable chunks of work, so a new COR—five years from now—will know what the heck each one of them represents
If an Activity represents work to be done by a single contractor, the Start Date Projected and Completion Date Projected should match those of the anticipated contract year, to aid “Actual % Complete" reporting

## Slide 25: “Activities” In OPPM - 2
If an Activity represents work to be done by multiple contractors, it should be split, so each contract is represented by a separate Activity, again to facilitate reporting
If a contract is awarded "late," then—at the next re-baselining—change the Activity’s Start Date Projected and Completion Date Projected to match the actual contract date, to support reporting
Once a “Total Costs Actual ” for an Activity has been reported to the IT Dashboard, OMB will not allow changes to its data
  Do *NOT* select in the Send Actual Costs To Dashboard column a “yes,” unless you have received and approved the final invoice for the tasks associated with that Activity; *DO* select “No”
  Otherwise, leave the Send Actual Costs To Dashboard field blank until all costs are accounted for, so you’ll be able to update the data

## Slide 26: Reporting: OMB IT Dashboard
HHS monthly extracts data from PMT, and sends the files to OMB on:
  EVM
  Other Performance Indicators
  Contracts
  HHS CIO Evaluation Ratings
  GAO Reports
OMB promotes updated version to production
http://www.itdashboard.gov | HHS | CMS

## Slide 27: Watch Lists
HHS High Variance List based on DME Variances...and:
  Cost or schedule variances ≥ ±10%
    Corrective action plan required
  Data ≥ 45 days old ("as of" date for EVM reporting),
  Data not updated (date on which you are completing this report) ≥ 45 days old
  Security and privacy factors
OMB Management Watch List based on Total Variances

## Slide 28: Summary: EVM Reporting Requirements
OMB: Explain ≥ ±10% variance
HHSAR: *If major* development, then: Compliant EVMS, monthly report, IBR, [for O&M] annual operational analysis
HHS CPIC: Monthly cost and schedule reporting...all IT projects
  Update OPPM each month: EVM and other performance
  Extracts monthly data to OMB for IT Dashboard
CMS: Update OPPM by *10th of each month*
  Total Costs Actual
  Planned % Complete
  Actual % Complete
  Start Date Projected
  Completion Date Projected
   ±10% variance requires corrective action plan
  Zero variance requires statement